## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Write SRS in correct format | Title must be centered, product overview must have indent | 1 |  | Closed | CuongTNQ | 2022-05-30 | 2023-06-06 | iter2 | SRS1, 2_Done | All
Add picture in sign up screen in SRS | Sign up screen misses 1 picture, need to add in | 2 |  | Closed | NhatTQ | 2022-05-30 | 2023-06-06 | iter2 | SRS2, 2_Done | Sign in
Customer's generate invoice screen needs to add multiple items | User must be able to make a invoice with multiple item one time only, without having to make a invoice multiple times | 3 |  | Closed | NhatTQ | 2022-06-14 | 2023-06-23 | iter3 | Task, 3_Done | Generate invoice
Customer's view transaction history screen needs to include bank saving changes | User must be able to view when and how much a bank saving is made or taken out | 4 |  | Closed | NhatTQ | 2022-06-27 | 2023-07-04 | iter4 | Task, 4_Done | View transaction history
Customer's request bank savings screen needs to change the rate | The rate should be changed to month and not year | 5 |  | Closed | CuongTNQ | 2022-06-27 | 2023-07-04 | iter4 | Task, 4_Done | Request bank savings