## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Sign up | Sign up | Guest | Guest want to sign up account on the system | NhatTQ | Done | iter1 | none
2 | Sign in | Sign in | Customer | Customer can sign in account on the system | CuongTNQ | Done | iter1 | none
3 | Log out | Log out | Customer | The customer logs out and is now determined as Guest. The guest is provided access to only see the homepage | CuongTNQ | Done | iter1 | none
4 | Change password | Change password | Customer | Customer want to change password for their account | DungTA | Done | iter1 | none
5 | Forgot password | Forgot password | Customer | Customer can reset their account password | TuHA | Done | iter1 | none
6 | Change pin number | Change pin number | Customer | Customer can change pin number | NhatTQ | Done | iter1 | none
7 | View personal information | View personal information | Customer | Customer can view their account information | DungTA | Done | iter3 | none
8 | Request to change personal information | Request to change personal information | Customer | Customer can make a request to change account information | DungTA | Done | iter3 | none
9 | Transfer money | Transfer money | Customer | Let customer transfer money from their account to another account in the same bank | TuHA | Done | iter2 | none
10 | View transaction history | View transaction history | Customer | Let customer view various types of transaction from their account and how their account balance changed | NhatTQ | Done | iter3 | iter4
11 | Generate invoice | Generate invoice | Customer | Let customer create an invoice | NhatTQ | Done | iter2 | iter3
12 | Pay invoice | Pay invoice | Customer | Let customer pay an invoice | NhatTQ | Done | iter2 | none
13 | Request locking account | Request locking account | Customer | Customer can send a request to lock account | TuHA | Done | iter3 | none
14 | Request bank savings | Request bank savings | Customer | Let customer make a request to create a bank savings | CuongTNQ | Done | iter3 | iter4
15 | Staff login | Staff login | Staff | Staff can log in to the system | CuongTNQ | Done | iter2 | none
16 | View customers’ information | View customers’ information | Staff | Staff can view information of all customers | DungTA | Done | iter3 | none
17 | Delete customers’ information | Delete customers’ information | Staff | Staff can delete a customer's account | DungTA | Done | iter4 | Done
18 | Process customer request | Process customer request | Staff | Staff can approve or reject a customer's request | DungTA | Done | iter3 | none
19 | [5 empty] | Done
20 | [5 empty] | Done
21 | [5 empty] | Done
22 | [5 empty] | Done
23 | [5 empty] | Done
24

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Sign up | Sign up | Guest want to sign up account on the system | NhatTQ | Done | II.3 | III.5
2 | Sign in | Sign in | Customer can sign in account on the system | CuongTNQ | Done
3 | Log out | Log out | The customer logs out and is now determined as Guest. The guest is provided access to only see the homepage | CuongTNQ | Done
4 | Change password | Change password | Customer want to change password for their account | DungTA | Done
5 | Forgot password | Forgot password | Customer can reset their account password | TuHA | Done | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document