## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Sign up | Sign up | Guest | Guest want to sign up account on the system | NhatTQ | Done | iter1 | none
2 | Sign in | Sign in | Customer | Customer can sign in account on the system | CuongTNQ | Done | iter1 | none
3 | Log out | Log out | Customer | The customer logs out and is now determined as Guest. The guest is provided access to only see the homepage | CuongTNQ | Done | iter1 | none
4 | Change password | Change password | Customer | Customer want to change password for their account | DungTA | Done | iter1 | none
5 | Forgot password | Forgot password | Customer | Customer can reset their account password | TuHA | Done | iter1 | none
6 | Change pin number | Change pin number | Customer | Customer can change pin number | NhatTQ | Done | iter1 | none
7 | View personal information | View personal information | Customer | Customer can view their account information | DungTA | Done | iter3 | none
8 | Request to change personal information | Request to change personal information | Customer | Customer can make a request to change account information | DungTA | Done | iter3 | none
9 | Transfer money | Transfer money | Customer | Let customer transfer money from their account to another account in the same bank | TuHA | Done | iter2 | none
10 | View transaction history | View transaction history | Customer | Let customer view various types of transaction from their account and how their account balance changed | NhatTQ | Done | iter3 | iter4 | User must be able to view when and how much a bank saving is made or taken out
11 | Generate invoice | Generate invoice | Customer | Let customer create an invoice | NhatTQ | Done | iter2 | iter3 | User must be able to make a invoice with multiple items one time only, without having to make a invoice multiple times
12 | Pay invoice | Pay invoice | Customer | Let customer pay an invoice | NhatTQ | Done | iter2 | none
13 | Request locking account | Request locking account | Customer | Customer can send a request to lock account | TuHA | Done | iter3 | none
14 | Request bank savings | Request bank savings | Customer | Let customer make a request to create a bank savings | CuongTNQ | Done | iter3 | iter4 | The rate should be changed to month and not year
15 | Staff login | Staff login | Staff | Staff can log in to the system | CuongTNQ | Done | iter2 | none
16 | View customers’ information | View customers’ information | Staff | Staff can view information of all customers | DungTA | Done | iter3 | none
17 | Process customer request | Process customer request | Staff | Staff can approve or reject a customer's request | DungTA | Done | iter3 | none
18 | Add staff account | Add staff account | Manager | Manager can add a staff account | CuongTNQ | Done | iter4 | none
19 | View VIP customer | View VIP customer | Manager | Manager can view a list a VIP Customer | TuHA | Done | iter4 | none
20 | Remove VIP status from customer | Remove VIP status from customer | Manager | Manager can remove VIP Status from a customer | TuHA | Done | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View personal information | View personal information | Customer can view their account information | DungTA | Done | II.2.2 UC-01 | II.1
2 | Sign in | Sign in | Customer can sign in account on the system | CuongTNQ | Done | II.2.2 UC-02 | II.2
3 | Log out | Log out | The customer logs out and is now determined as Guest. The guest is provided access to only see the homepage | CuongTNQ | Done | II.2.2 UC-03 | II.3
4 | Change password | Change password | Customer want to change password for their account | DungTA | Done | II.2.2 UC-04 | II.4
5 | Forgot password | Forgot password | Customer can reset their account password | TuHA | Done | II.2.2 UC-05 | II.5
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Transfer money | Transfer money | Let customer transfer money from their account to another account in the same bank | TuHA | Done | II.2.2 UC-09 | II.9
2 | Generate invoice | Generate invoice | Let customer create an invoice | NhatTQ | Done | II.2.2 UC-11 | II.11
3 | Pay invoice | Pay invoice | Let customer pay an invoice | NhatTQ | Done | II.2.2 UC-12 | II.12
4 | Staff login | Staff | Staff can log in to the system | CuongTNQ | Done | II.2.2 UC-15 | II.15
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View personal information | View personal information | Customer can view their account information | DungTA | Done | II.2.2 UC-07 | II.7
2 | Request to change personal information | Request to change personal information | Customer can make a request to change account information | DungTA | Done | II.2.2 UC-08 | II.8
3 | View transaction history | View transaction history | Let customer view various types of transaction from their account and how their account balance changed | NhatTQ | Done | II.2.2 UC-10 | II.10
4 | Request locking account | Request locking account | Customer can send a request to lock account | TuHA | Done | II.2.2 UC-13 | II.13
5 | Request bank savings | Request bank savings | Let customer make a request to create a bank savings | CuongTNQ | Done | II.2.2 UC-14 | II.14
6 | View customers’ information | View customers’ information | Staff can view information of all customers | DungTA | Done | II.2.2 UC-16 | II.16
7 | Process customer request | Process customer request | Staff can approve or reject a customer's request | DungTA | Done | II.2.2 UC-17 | II.17
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Add staff account | Add staff account | Manager can add a staff account | CuongTNQ | Done | II.2.2 UC-18 | II.18
2 | View VIP customer | View VIP customer | Manager can view a list a VIP Customer | TuHA | Done | II.2.2 UC-19 | II.19
3 | Remove VIP status from customer | Remove VIP status from customer | Manager can remove VIP Status from a customer | TuHA | Done | II.2.2 UC-20 | II.20
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document